## Alignment-Matrix-Simplified
Alignment Matrix
Project Goals (Strategies) |  | Magnitude/Target value | Estimated Cost | Cost Justification | Reference Strategies (Goals) | [11 empty] | Analysis | Value/Points | Justification of Issues
[5 empty] | 1 | Follow standard business processes | 2 | Prevent cases from not being handled | 3 | Share information with agencies | 4 | Promote information provision about the policy owner between claim department and sales department | 5 | Be aware of payment deadlines for dealing with customer (legally based) | 6 | Property insurance: Identify appropriate level of damages
|  |  |  | Value/Points |  | 50 |  | 100 |  | 50 |  | 25 |  | 75 |  | 75 |  | 375
1 | Validate data entries for being compliant with business processes | - | 500000 | - | A | Standard process defines certain output to be delivered | [10 empty] | 1 | 50
2 | Establish a mechanism for automatically checking unhandeled cases and create warning messages to responsible person | - | 1000000 | - |  |  | C | Obvious | [8 empty] | 1 | 100
3 | Establish automatic data synchroization mechanisms with agencies | - | 1000000 | - |  |  |  |  | C | Obvious | [6 empty] | 1 | 50
4 | Establish common unified information repository between claim and sales department | - | 5000000 | New architecture needed for sharing information | [6 empty] | C | Obvious |  |  |  |  | 1 | 25
5 | Improve usability of user interface for entering policy owner data | - | 1000000 | UI experts must be involved | [12 empty] | 0 | 0
|  |  | 8500000 |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 0 |  | 0 |  | 45
Justification of Issues | [12 empty] | A | Not relevant for project | C | Not relevant for project
Alignment Statistics
A | Unaligned Project Goals | 1
B | Not Addressed Reference Strategies (Goals) | 2
C | Overall Cost | 8500000
D | Unaligned Cost | 1000000
E | # Assumptions (Unknown) | 1
F | # Context Data (Known) | 3
G | Project Goals Alignment Gap | 20%
H | Reference Strategies Alignment Gap | 33.33%
I | Cost Alignment Ratio | 88.24%
J | Alignment Risk (% Unknown) | 25%
K | Project value | 12%